## Sheet1
Task ID | Task Name | Start Date | Duration (days) | End Date | Appointee | Gantt Chart (Weeks)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D1 | Project Group & Topic Form |  |  | 2021-09-26 | All
D2 | Project Proposal & Outline |  |  | 2021-10-10 | All
1 | DATA PREPROCESSING STAGE | 2021-10-11 | 12 | 2021-10-22 | Caridad, Luis
1.1 | DATA CLEANING | 2021-10-11 | 4 | 2021-10-14 | Luis
1.1.1 | Handle missing values | 2021-10-11 | 2 | 2021-10-12 | Luis
1.1.2 | Deal with noisy data & anomalies | 2021-10-13 | 2 | 2021-10-14 | Luis
1.2 | DATA REDUCTION | 2021-10-15 | 5 | 2021-10-19 | Caridad, Luis
1.2.1 | Study approach A: reduce to less states | 2021-10-15 | 5 | 2021-10-19 | Caridad
1.2.2 | Study approach B: shrinking methods | 2021-10-15 | 5 | 2021-10-19 | Luis
1.3 | DATA TRANSFORMATION | 2021-10-20 | 4 | 2021-10-23 | Caridad
1.3.1 | Select most appropiate data classes | 2021-10-20 | 2 | 2021-10-21 | Caridad
1.3.2 | Aggregation | 2021-10-22 | 2 | 2021-10-23 | Caridad
1.3.3 | Discretization & normalization | 2021-10-22 | 2 | 2021-10-23 | Caridad
2 | DATA EXPLORATION STAGE | 2021-10-24 | 8 | 2021-10-31 | Kemen
2.1 | STATISTICS | 2021-10-24 | 3 | 2021-10-27 | Kemen
2.1.1 | Correlation matrix | 2021-10-24 | 3 | 2021-10-27 | Kemen
2.1.2 | Average of accidents per day | 2021-10-24 | 3 | 2021-10-27 | Kemen
2.1.3 | 5-number summaries of the predictors | 2021-10-24 | 3 | 2021-10-27 | Kemen
2.2 | VISUALIZATIONS | 2021-10-28 | 3 | 2021-10-31 | Kemen
2.2.1 | Number of accident and severity over the location | 2021-10-28 | 3 | 2021-10-31 | Kemen
2.2.2 | Number of accident and severity over the time of the day | 2021-10-28 | 3 | 2021-10-31 | Kemen
2.2.3 | Number of accident and severity over multiple weather factors: Temperature, Humidity, Wind | 2021-10-28 | 3 | 2021-10-31 | Kemen
2.2.4 | Number of accident and severity over the month | 2021-10-28 | 3 | 2021-10-31 | Kemen
2.2.5 | Histogram of the weather condition | 2021-10-28 | 3 | 2021-10-31 | Kemen
D3 | Project Plan & Detail |  |  | 2021-11-07 | All
3 | DATA MINING STAGE | 2021-11-01 | 26 | 2021-11-26 | All
3.1 | FEATURE SELECTION (on TRAIN set) | 2021-11-01 | 7 | 2021-11-07 | Kemen, Luis
3.1.1 | Test/Train split | 2021-11-01 | 1 | 2021-11-01 | Luis
3.1.2 | Multicollinearity evaluation | 2021-11-02 | 6 | 2021-11-07 | Luis
3.1.3 | Predictors' significance evaluation | 2021-11-02 | 6 | 2021-11-07 | Luis
3.1.4 | Predictors' behaviour evaluation | 2021-11-02 | 6 | 2021-11-07 | Kemen
3.1.5 | (Non-)Linearity evaluation | 2021-11-02 | 6 | 2021-11-07 | Luis
3.2 | CLASSIFICATION | 2021-11-08 | 8 | 2021-11-15 | Caridad
3.2.1 | Build model | 2021-11-08 | 4 | 2021-11-11 | Caridad
3.2.2 | Fit model (on TEST set) | 2021-11-12 | 4 | 2021-11-15 | Caridad
3.3 | MODEL SELECTION | 2021-11-16 | 3 | 2021-11-18 | Caridad
3.3.1 | Apply resampling methods: CV | 2021-11-16 | 3 | 2021-11-18 | Caridad
3.4 | MODEL EVALUATION | 2021-11-19 | 8 | 2021-11-26 | Kemen
3.4.1 | Analyze confusion matrix | 2021-11-19 | 5 | 2021-11-23 | Kemen
3.4.2 | Analyze ROC curves | 2021-11-24 | 3 | 2021-11-26 | Kemen
4 | EVALUATION/INTERPRETATION STAGE | 2021-11-27 | 4 | 2021-11-30 | All
4.1.1 | Write report | 2021-11-27 | 4 | 2021-11-30 | All
4.1.2 | Design presentation | 2021-11-27 | 4 | 2021-11-30 | All
D4 | Project Presentation & Report |  |  | 2021-12-01 | All